## June 2024
Project# | Title | Dept or Login Dept | User/User Group | Dept Owner | Date Started | Expected Completion | Estimated Work Effort (hours) | Actual Hours Spent (Cumulative) | Comments | Goal
| Ambient Scribing: Time in Inbox |  |  | Prof. Ming Tai-Seale | 2024-06-01 | 2024-10-01 | 40 | 8 | 6/27/2024: Rec'd detailed specs. | Show statistics for physicians time using Inbox tools during and after normal clinic hours.
| Ambient Scribing: Time in Notes |  |  | Prof. Ming Tai-Seale | 2024-06-01 | 2024-08-01 | 40 | 24 | 6/26/24: Delivered draft data showing active writing/editing time. | Show statistics for time physicians spend writing/editing progress notes during and after normal clinic hours.
| Concierge for All: Colorectal Cancer Screening |  |  | Dr. Laurel Dang | 2024-06-01 | 2024-09-01 | 100 | 20 | 6/27/24: Started working with health maintenance tables. | Develop a dashboard to show primary care physicians their patients' completion rate of colorectal cancer screenings.
| Concierge for All: GI triage notes |  |  | Dr. Thomas Savides | 2024-06-01 | 2024-09-01 | 40 | 0 |  | Show statistics for selected GI physicians' creation of interventional triage notes.
| Concierge for All: Propofol and ride share |  |  | Dr. Thomas Savides | 2024-06-01 | On hold | 40 | 20 | 6/26/24: Not clear from the data that the check-up calls are being made and documented per protocol. | Collect statistics on safety of ride share protocol following propofol sedation during colonoscopies: number of patients using the protocol and the number who report problems during the safety phone call.
| Open and Ask mobile app development |  |  | Prof. Ming Tai-Seale | 2024-06-01 | 2024-11-01 | 200 | 8 | 6/27/24: Downloaded code from developer. Set up new GitHub repository to host the code. Have applied for Amazon Web Services (AWS) account via Campus IT. | Deploy tool for physicians to use to improve communcation with patients.
80

## February 2025
Status | Project# | Title | Dept or Login Dept | User/User Group | Dept Owner | Date Started | Expected Completion | Estimated Work Effort (hours) | Actual hours this month | Actual Hours Spent (Cumulative) | Comments | Goal
|  | Augmented Reply Technology |  |  | Prof. Ming Tai-Seale | 2024-12-01 | 2025-03-01 | 100 | 42 | #REF! | 1/2/25: Compiled & de-identified (by hand) sample messages. 1/3/25: Looking into how to break up message threads. 1/6/25: Developing automatic formatting app. 1/10/25: Producing list of first use of ART for physicians in boot camp. 1/28/25: Producing list of which departments have physicians who've used ART. 2/12/25: Developed Excel Add-In to extract original message in forwarded thread. 2/14/25: Delivered ART messages. 2/20/25: Merged before/after-unassisted and after-assisted messages into one Excel sheet, at Courtney's request. 2/26/25: Investigating drop in message numbers; improved algorithm for extracting inner message from thread. 2/27/25: Delivered sample messages. 2/28/25: Drafted algorithm description document. | ACQUIRE project to study effect of AI message-drafting technology on patient's perception of physician messaging
|  | AI Notetaker: Documentation |  |  | Prof. Ming Tai-Seale | 2024-07-01 | 2024-08-01 | 80 | 0 | #REF! | 7/23/24: Produced list of number of half-days on which selected physicians had office appointments. 8/15/24: In response to question, produced list of the selected physicians who had seen patients in Express/Urgent Care. 8/30/24: Reran extraction using new physicians list. 9/4/24: Revised code re: Express/Urgent Care per Andrew's questions. 9/30/24: Produced new combined spreadsheet per Andrew's request using latest physicians list. 10/1/24: Added new fields for use of interpreters, Haiku. 10/11/24: Reviewed results in light of Dr. Wilkinson's questioning her appt data. 10/21/24: Investigated lists of outpatient clinics, at Dr. Chua's request. 11/18/24: Meeting 1/10/25: Producing list of clinics at which physicians had office visits. 1/28/25: Producing new list of clinics for new list of physicians. Since this seems to be needed frequently, created Excel app to look up physician names from UCSD Blink using email addresses, reducing manual work. | Reduce physician workload through AI drafting of documentation.
|  | AI Notetaker: Time in Inbox |  |  | Prof. Ming Tai-Seale | 2024-06-01 | 2024-10-01 | 100 | 0 | #REF! | 6/27/24: Rec'd detailed specs. 7/10/24: Rec'd data from Epic. 7/18/24: Building SQL query to compute read, reply times. 7/31/24: Comparing my results w/ Epic-provided data. 8/1/24: Started documentation on GitLab project page. 8/2/24: Reviewed latest data from Epic & made changes to my SQL code to get more precise msg sent times (not truncated to the minute). Also found possible error in their turnaround time computation & alerted Evan. 8/5/24: Reviewing Epic data & understanding their linkages between MyChart and InBasket message IDs. 8/7/24: Adding physician workload statistics. 8/14/24: Expanding # of messages pulled & comparing with Epic data. 9/3/24: Edited list of data variables & worked with Evan at Epic to understand how to pull text of messages. 10/4/24: Investigating selected messages that seem not to have been answered. 11/5/24: Further investigation of selected messages. 12/13/24: Extracting msgs from before and after physician first used automatic reply technology. 12/20/24: Improving method of linking messages with physicians, increasing # of messages. | Show statistics for physicians time using In Basket tools during and after normal clinic hours.
|  | AI Notetaker: Time in Notes |  |  | Prof. Ming Tai-Seale | 2024-06-01 | 2024-08-01 | 80 | 0 | #REF! | 7/5/24: Investigated differences between NOTE_WRITE_TIMING and UAL_ACTIVITY_HOURS approaches. 7/11/24: Delivered combined data set. 8/2/24: Produced new dataset for just the specific physicians on Amanda's list and delivered to Courtney. This new dataset included the device preference (Apple or Android) for each. 10/15/24: Reviewed results in light of Dr. Wilkinson's comments about difference between her appt records & # of rows for her in "control group" spreadsheet. | Show statistics for time physicians spend writing/editing progress notes during and after normal clinic hours.
|  | Concierge for All: Value of Colorectal Cancer Screening |  |  | Dr. Thomas Savides | 2024-08-01 | 2024-09-01 | 40 | 0 | #REF! | 8/15/24: Started 8/16/24: Shared preliminary results w/ Dr. Savides. Added colonoscopy notes. 8/29/24: Reviewed results w/ Drs. Savides, Dang. | Quantify the value of screening tests: how many cancers do we detect through tests like COLOGUARD?
|  | Concierge for All: Call volume |  |  | Dr. Thomas Savides | 2025-02-01 | 2025-04-01 | 80 | 10 | 10 | 2/18/25: Initial coding of call volume estimation. 2/19/25: Improving filtering of encounters using associated notes.
In Progress |  | Concierge for All: Colorectal Cancer Screening |  |  | Dr. Laurel Dang | 2024-06-01 | 2024-09-01 | 100 | 0 | #REF! | 7/3/24: Reviewed results w/ Dr. Savides & revised per his comments. Need mtg w/ Tableau team to turn this into a dashboard. 8/7/24: Looks like Tableau team has already built everything. 8/8/24: Shifting to SQL query to extract the variables rec'd from Ross. 8/29/24: Reviewed preliminary results with Drs. Savides, Dang. 8/30/24: Revising code following review. 9/4/24: Delivered new results using revised ICD-10 codes, restricting to UCSD physicians and patients. 10/18/24: Extended dashboard to San Diego Sports Medicine physicians. 11/14/24: Extended dashboard to IGO group physicians. 11/22/24: Investigated number of CRC screening tests for IGO physicians and patients. 1/16/25: Pulled new stats for Graham; worked with Tableau people to get access to usage stats. | Develop a dashboard to show primary care physicians their patients' completion rate of colorectal cancer screenings.
|  | Concierge for All: GI triage notes |  |  | Dr. Thomas Savides | 2024-06-01 | 2025-03-01 | see next row | see next row | see next row | 7/5/24: Built initial query 10/30/24: Used Dr. Kwan's code to improve extraction of triage notes; included source of referral request. 11/6/24: Delivered data to Courtney. 11/7/24: Extracted & delivered activity log data from Tom's live triage experiment. 11/8/24: Experimented w/ linking messages to triaging provider using IB_MESSAGES to MYC_MESG.TO_USER_ID column. (Wasn't useful--TO_USER_ID often doesn't point to triaging physician.) 11/13/24: Revised triage notes to correct error that occurs when record is closed & immediately reopened. 11/18/24: Produced list of GI triage note writers for patient experience folks. 11/21/24: Incorporated on-call status into spreadsheet. 11/25/24: Built tool to automatically generate SQL-friendly input from on-call list (for future use). 11/26/24: Adding variables to triage notes & releasing new version 12/3/24: Investigating add'l triage smart elements. 12/4/24: Investigating time-in-record values. 12/10/24: Investigating possible fix to zero-length time-in-record events. 12/23/24: Tweaking code to improve pairing of access log events.
In Progress |  | Concierge for All: GI triage notes |  |  | Dr. Thomas Savides | 2024-06-01 | 2025-03-01 | 200 | 48 | #REF! | 1/3/25: Working on finding source of triage request. 1/7/25: Investigating triage note length of time in record outliers. 1/10/25: Investigating excessive note edit times. 1/13/25: Fixing #colonoscopies. 1/14/25: Adding work RVU, #colonoscopies, #clinic days to triage notes. 1/29/25: Adding insurance, length of note to triage notes. Investigated & fixed problem with excessive edit times. 1/26/25: Delivered wRVU data to Tom for his review. 1/30/25: Revised work hours code to use actual appointments instead of fixed hours. Delivered estimated hours to Tom for his review. 2/3/25: Revising time in triage notes to form new start/stop pairs when patient encounter changes. 2/7/25: Extracted triage request messages & triage notes for CS student. Wrote C# app to deidentify dates in messages. 2/11/25: Further developed deidentification app. | Show statistics for selected GI physicians' creation of interventional triage notes.
|  | Concierge for All: Message response time |  |  | Dr. Thomas Savides | 2024-06-01 | 2025-03-01 | 100 | 16 | 16 | 1/23/25: Developing code to extract patient messages and matching with physician replies. 2/14/25: Delivered data set.
|  | Concierge for All: Symptom calls |  |  | Dr. Thomas Savides | 2025-02-01 | 2025-04-01 | 80 | 36 | 36 | 2/18/25: Initial coding of call volume estimation. 2/19/25: Improving filtering of encounters using associated notes. 2/26/25: Adding detection of treatment plans using notes parsing. 2/28/25: Investigating detection of symptom keywords in notes.
In Progress |  | Concierge for All: Propofol and ride share |  |  | Dr. Thomas Savides | 2024-06-01 | On hold | 40 | 0 | #REF! | 6/26/24: Not clear from the data that the check-up calls are being made and documented per protocol. 7/11/24: Dr. Savides held meeting to clarify procedures w/ clinical staff. ON HOLD until new procedures developed & in place. 1/15/25: Investigating use of new "GI Car Service Protocol" button. 1/16/25: Delivered "GI Car Service Protocol" to Tom Savides. | Collect statistics on safety of ride share protocol following propofol sedation during colonoscopies: number of patients using the protocol and the number who report problems during the safety phone call.
|  | Concierge for All: What's Keeping Gastroenterologists Busy? |  |  | Dr. Thomas Savides | 2024-10-01 | 2024-12-01 | 60 | 0 | #REF! | 10/21/24: Reviewed & adapted Dr. Kwan's code re: triage notes Experimented with physician, clinic availablity Investigated Relative Value Units. 10/24/24: Investigated UCSD-specific table TDS_3NA_EA_PROD 11/1/24: Built app to split up availability data by physician. 11/4/24: Delivered third-next available appt data to Courtney for review. 11/5/24: Investigating time-to-surgery for data on colonoscopy availability. 11/7/24: Delivered expanded third-next available appt data to Courtney, now including ALL appt lengths. Also delivered time-to-surgery spreadsheet. 11/8/24: Improving Excel Add-In app to split availability data into separate worksheets. 11/19/24: Delivered RVU data. 11/21/24: Researched UCSD-specific RVU tables. 11/25/24: Delivered revised RVU data w/ more procedures. 11/16/24: Developing tracker for statistical analysis plan variables.
In Progress |  | Open and Ask mobile app development |  |  | Prof. Ming Tai-Seale | 2024-06-01 | 2024-11-01 | 200 | 0 | #REF! | 7/9/24: Met w/ key players to get cloud services through Health AWS services. 7/19/24: Obtained Macbook for code development; completed Swift language programming tutorial. 7/26/24: Met w/ ACTRI cloud team to review progress: they've got EC2 instance running and have started creating Docker container there. 8/2/24: Cloud database, cache and storage all in place. Next step is to get the EC2 instance communicating w/ these new pieces. Also will be creating an AWS VRD for my use in development & testing. 8/26/24: Working on compiling Swift code on MacBook. 9/9/24: Prototyped user management app. 9/12/24: Prepared for & participated in ThinkShop meeting. 10/22/24: Participated in ThinkShop office hours. 10/23/24: Experimented with app in MacBook. 11/8/24: Reviewed React code & conferring with ACTRI cloud engineer re: possible error. 11/12/24: Edited login code on VRD in preparation for this week's trial run. Prepared for installation of app user management tool in VRD. 11/13/24: Met online with ACTRI cloud engineer to debug app. Met online with ACTRI AWS engineer to get app user management tool running in Python on VRD. 11/14/24: Online trouble-shooting with ACTRI cloud engineer. 11/18/24: Revising user management app to match password hashing used in Open and Ask backend code. | Deploy tool for physicians to use to improve communcation with patients.
|  | Publication tracking app |  |  | Courtney, Ross | 2024-07-01 | 2024-07-01 | 24 | 0 | #REF! | 7/15/24: Demonstrated new Qualtrics site to Courtney. | Build UCSD-labeled online site for researchers to enter their publications into a database.
|  | LHS Center: Advanced Care Planning |  |  | Prof. Ming Tai-Seale | 2024-11-01 | 2024-11-01 | 12 | 0 | #REF! | 11/12/24: Extracted & deidentified sample ACP progress notes.
|  | LHSS ESTaR: Peripheral Artery Disease |  |  | Dr. Mattheus Ramsis | 2024-10-01 | 2024-12-01 | 80 | 0 | #REF! | 10/4/24: Prototyped code & reviewed preliminary results w/ PI. Sent suggested diagnostic codes, medication codes to PI for review. 10/9/24: Developed C# Excel Add-In to parse patient lab reports & extract key diagnostic indices into SQL code that can be combined with demographics and lab data. 10/14/24: Revised data extraction to incorporate changes from 10/11 review: * add chronic kidney disease, lupus & scleroderma to comorbidities * add A1C to labs * add lower extremity angiogram results * add smoking history * revise presentation of lab data 10/21/24: Added new proc codes from Dr. Ross. | Gather data in support of clinical measurements of periheral arterial flow device.

## March 2025
Status | Project# | Title | Dept or Login Dept | User/User Group | Dept Owner | Date Started | Expected Completion | Estimated Work Effort (hours) | Actual hours this month | Actual Hours Spent (Cumulative) | Comments | Goal
|  | Augmented Reply Technology |  |  | Prof. Ming Tai-Seale | 2024-12-01 | 2025-03-01 | 100 | 0 | #REF! | 1/2/25: Compiled & de-identified (by hand) sample messages. 1/3/25: Looking into how to break up message threads. 1/6/25: Developing automatic formatting app. 1/10/25: Producing list of first use of ART for physicians in boot camp. 1/28/25: Producing list of which departments have physicians who've used ART. 2/12/25: Developed Excel Add-In to extract original message in forwarded thread. 2/14/25: Delivered ART messages. 2/20/25: Merged before/after-unassisted and after-assisted messages into one Excel sheet, at Courtney's request. 2/26/25: Investigating drop in message numbers; improved algorithm for extracting inner message from thread. 2/27/25: Delivered sample messages. 2/28/25: Drafted algorithm description document. | ACQUIRE project to study effect of AI message-drafting technology on patient's perception of physician messaging
|  | AI Notetaker: Documentation |  |  | Prof. Ming Tai-Seale | 2024-07-01 | 2024-08-01 | 80 | 0 | #REF! | 7/23/24: Produced list of number of half-days on which selected physicians had office appointments. 8/15/24: In response to question, produced list of the selected physicians who had seen patients in Express/Urgent Care. 8/30/24: Reran extraction using new physicians list. 9/4/24: Revised code re: Express/Urgent Care per Andrew's questions. 9/30/24: Produced new combined spreadsheet per Andrew's request using latest physicians list. 10/1/24: Added new fields for use of interpreters, Haiku. 10/11/24: Reviewed results in light of Dr. Wilkinson's questioning her appt data. 10/21/24: Investigated lists of outpatient clinics, at Dr. Chua's request. 11/18/24: Meeting 1/10/25: Producing list of clinics at which physicians had office visits. 1/28/25: Producing new list of clinics for new list of physicians. Since this seems to be needed frequently, created Excel app to look up physician names from UCSD Blink using email addresses, reducing manual work. | Reduce physician workload through AI drafting of documentation.
|  | AI Notetaker: Time in Inbox |  |  | Prof. Ming Tai-Seale | 2024-06-01 | 2024-10-01 | 100 | 0 | #REF! | 6/27/24: Rec'd detailed specs. 7/10/24: Rec'd data from Epic. 7/18/24: Building SQL query to compute read, reply times. 7/31/24: Comparing my results w/ Epic-provided data. 8/1/24: Started documentation on GitLab project page. 8/2/24: Reviewed latest data from Epic & made changes to my SQL code to get more precise msg sent times (not truncated to the minute). Also found possible error in their turnaround time computation & alerted Evan. 8/5/24: Reviewing Epic data & understanding their linkages between MyChart and InBasket message IDs. 8/7/24: Adding physician workload statistics. 8/14/24: Expanding # of messages pulled & comparing with Epic data. 9/3/24: Edited list of data variables & worked with Evan at Epic to understand how to pull text of messages. 10/4/24: Investigating selected messages that seem not to have been answered. 11/5/24: Further investigation of selected messages. 12/13/24: Extracting msgs from before and after physician first used automatic reply technology. 12/20/24: Improving method of linking messages with physicians, increasing # of messages. | Show statistics for physicians time using In Basket tools during and after normal clinic hours.
|  | AI Notetaker: Time in Notes |  |  | Prof. Ming Tai-Seale | 2024-06-01 | 2024-08-01 | 80 | 0 | #REF! | 7/5/24: Investigated differences between NOTE_WRITE_TIMING and UAL_ACTIVITY_HOURS approaches. 7/11/24: Delivered combined data set. 8/2/24: Produced new dataset for just the specific physicians on Amanda's list and delivered to Courtney. This new dataset included the device preference (Apple or Android) for each. 10/15/24: Reviewed results in light of Dr. Wilkinson's comments about difference between her appt records & # of rows for her in "control group" spreadsheet. | Show statistics for time physicians spend writing/editing progress notes during and after normal clinic hours.
|  | Concierge for All: Value of Colorectal Cancer Screening |  |  | Dr. Thomas Savides | 2024-08-01 | 2024-09-01 | 40 | 0 | #REF! | 8/15/24: Started 8/16/24: Shared preliminary results w/ Dr. Savides. Added colonoscopy notes. 8/29/24: Reviewed results w/ Drs. Savides, Dang. | Quantify the value of screening tests: how many cancers do we detect through tests like COLOGUARD?
|  | Concierge for All: Call volume |  |  | Dr. Thomas Savides | 2025-02-01 | 2025-04-01 | 80 | 0 | 10 | 2/18/25: Initial coding of call volume estimation. 2/19/25: Improving filtering of encounters using associated notes.
In Progress |  | Concierge for All: Colorectal Cancer Screening |  |  | Dr. Laurel Dang | 2024-06-01 | 2024-09-01 | 100 | 0 | #REF! | 7/3/24: Reviewed results w/ Dr. Savides & revised per his comments. Need mtg w/ Tableau team to turn this into a dashboard. 8/7/24: Looks like Tableau team has already built everything. 8/8/24: Shifting to SQL query to extract the variables rec'd from Ross. 8/29/24: Reviewed preliminary results with Drs. Savides, Dang. 8/30/24: Revising code following review. 9/4/24: Delivered new results using revised ICD-10 codes, restricting to UCSD physicians and patients. 10/18/24: Extended dashboard to San Diego Sports Medicine physicians. 11/14/24: Extended dashboard to IGO group physicians. 11/22/24: Investigated number of CRC screening tests for IGO physicians and patients. 1/16/25: Pulled new stats for Graham; worked with Tableau people to get access to usage stats. | Develop a dashboard to show primary care physicians their patients' completion rate of colorectal cancer screenings.
|  | Concierge for All: GI triage notes |  |  | Dr. Thomas Savides | 2024-06-01 | 2025-03-01 | see next row | 0 | #VALUE! | 7/5/24: Built initial query 10/30/24: Used Dr. Kwan's code to improve extraction of triage notes; included source of referral request. 11/6/24: Delivered data to Courtney. 11/7/24: Extracted & delivered activity log data from Tom's live triage experiment. 11/8/24: Experimented w/ linking messages to triaging provider using IB_MESSAGES to MYC_MESG.TO_USER_ID column. (Wasn't useful--TO_USER_ID often doesn't point to triaging physician.) 11/13/24: Revised triage notes to correct error that occurs when record is closed & immediately reopened. 11/18/24: Produced list of GI triage note writers for patient experience folks. 11/21/24: Incorporated on-call status into spreadsheet. 11/25/24: Built tool to automatically generate SQL-friendly input from on-call list (for future use). 11/26/24: Adding variables to triage notes & releasing new version 12/3/24: Investigating add'l triage smart elements. 12/4/24: Investigating time-in-record values. 12/10/24: Investigating possible fix to zero-length time-in-record events. 12/23/24: Tweaking code to improve pairing of access log events.
In Progress |  | Concierge for All: GI triage notes |  |  | Dr. Thomas Savides | 2024-06-01 | 2025-03-01 | 200 | 0 | #REF! | 1/3/25: Working on finding source of triage request. 1/7/25: Investigating triage note length of time in record outliers. 1/10/25: Investigating excessive note edit times. 1/13/25: Fixing #colonoscopies. 1/14/25: Adding work RVU, #colonoscopies, #clinic days to triage notes. 1/29/25: Adding insurance, length of note to triage notes. Investigated & fixed problem with excessive edit times. 1/26/25: Delivered wRVU data to Tom for his review. 1/30/25: Revised work hours code to use actual appointments instead of fixed hours. Delivered estimated hours to Tom for his review. 2/3/25: Revising time in triage notes to form new start/stop pairs when patient encounter changes. 2/7/25: Extracted triage request messages & triage notes for CS student. Wrote C# app to deidentify dates in messages. 2/11/25: Further developed deidentification app. | Show statistics for selected GI physicians' creation of interventional triage notes.
|  | Concierge for All: Message response time |  |  | Dr. Thomas Savides | 2024-06-01 | 2025-03-01 | 100 | 0 | 16 | 1/23/25: Developing code to extract patient messages and matching with physician replies. 2/14/25: Delivered data set.
|  | Concierge for All: Symptom calls |  |  | Dr. Thomas Savides | 2025-02-01 | 2025-04-01 | 80 | 0 | 36 | 2/18/25: Initial coding of call volume estimation. 2/19/25: Improving filtering of encounters using associated notes. 2/26/25: Adding detection of treatment plans using notes parsing. 2/28/25: Investigating detection of symptom keywords in notes.
In Progress |  | Concierge for All: Propofol and ride share |  |  | Dr. Thomas Savides | 2024-06-01 | On hold | 40 | 0 | #REF! | 6/26/24: Not clear from the data that the check-up calls are being made and documented per protocol. 7/11/24: Dr. Savides held meeting to clarify procedures w/ clinical staff. ON HOLD until new procedures developed & in place. 1/15/25: Investigating use of new "GI Car Service Protocol" button. 1/16/25: Delivered "GI Car Service Protocol" to Tom Savides. | Collect statistics on safety of ride share protocol following propofol sedation during colonoscopies: number of patients using the protocol and the number who report problems during the safety phone call.
|  | Concierge for All: What's Keeping Gastroenterologists Busy? |  |  | Dr. Thomas Savides | 2024-10-01 | 2024-12-01 | 60 | 0 | #REF! | 10/21/24: Reviewed & adapted Dr. Kwan's code re: triage notes Experimented with physician, clinic availablity Investigated Relative Value Units. 10/24/24: Investigated UCSD-specific table TDS_3NA_EA_PROD 11/1/24: Built app to split up availability data by physician. 11/4/24: Delivered third-next available appt data to Courtney for review. 11/5/24: Investigating time-to-surgery for data on colonoscopy availability. 11/7/24: Delivered expanded third-next available appt data to Courtney, now including ALL appt lengths. Also delivered time-to-surgery spreadsheet. 11/8/24: Improving Excel Add-In app to split availability data into separate worksheets. 11/19/24: Delivered RVU data. 11/21/24: Researched UCSD-specific RVU tables. 11/25/24: Delivered revised RVU data w/ more procedures. 11/16/24: Developing tracker for statistical analysis plan variables.
In Progress |  | Open and Ask mobile app development |  |  | Prof. Ming Tai-Seale | 2024-06-01 | 2024-11-01 | 200 | 0 | #REF! | 7/9/24: Met w/ key players to get cloud services through Health AWS services. 7/19/24: Obtained Macbook for code development; completed Swift language programming tutorial. 7/26/24: Met w/ ACTRI cloud team to review progress: they've got EC2 instance running and have started creating Docker container there. 8/2/24: Cloud database, cache and storage all in place. Next step is to get the EC2 instance communicating w/ these new pieces. Also will be creating an AWS VRD for my use in development & testing. 8/26/24: Working on compiling Swift code on MacBook. 9/9/24: Prototyped user management app. 9/12/24: Prepared for & participated in ThinkShop meeting. 10/22/24: Participated in ThinkShop office hours. 10/23/24: Experimented with app in MacBook. 11/8/24: Reviewed React code & conferring with ACTRI cloud engineer re: possible error. 11/12/24: Edited login code on VRD in preparation for this week's trial run. Prepared for installation of app user management tool in VRD. 11/13/24: Met online with ACTRI cloud engineer to debug app. Met online with ACTRI AWS engineer to get app user management tool running in Python on VRD. 11/14/24: Online trouble-shooting with ACTRI cloud engineer. 11/18/24: Revising user management app to match password hashing used in Open and Ask backend code. | Deploy tool for physicians to use to improve communcation with patients.
|  | Publication tracking app |  |  | Courtney, Ross | 2024-07-01 | 2024-07-01 | 24 | 0 | #REF! | 7/15/24: Demonstrated new Qualtrics site to Courtney. | Build UCSD-labeled online site for researchers to enter their publications into a database.
|  | LHS Center: Advanced Care Planning |  |  | Prof. Ming Tai-Seale | 2024-11-01 | 2024-11-01 | 12 | 0 | #REF! | 11/12/24: Extracted & deidentified sample ACP progress notes.
|  | LHSS ESTaR: Peripheral Artery Disease |  |  | Dr. Mattheus Ramsis | 2024-10-01 | 2024-12-01 | 80 | 0 | #REF! | 10/4/24: Prototyped code & reviewed preliminary results w/ PI. Sent suggested diagnostic codes, medication codes to PI for review. 10/9/24: Developed C# Excel Add-In to parse patient lab reports & extract key diagnostic indices into SQL code that can be combined with demographics and lab data. 10/14/24: Revised data extraction to incorporate changes from 10/11 review: * add chronic kidney disease, lupus & scleroderma to comorbidities * add A1C to labs * add lower extremity angiogram results * add smoking history * revise presentation of lab data 10/21/24: Added new proc codes from Dr. Ross. | Gather data in support of clinical measurements of periheral arterial flow device.
0
24
24